## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Audit Checklist Module AC : It'll give me list of questions for the UI | Create Repository :- CheckList GetQuestionsList(): HttpGet for retrieve List of Questions |  | 2020-09-21 | 2020-09-21 | 3 | 3 | 0 | Supriya Sinha | Completed
| Create End Point:- AuditCheckList Get(): HttpGet for invoking Checklist Log4Net for logging |  | 2020-09-21 | 2020-09-21 | 3 | 3 | 0 | Supriya Sinha | Completed
| In Memory Database (Create list of Questions) |  | 2020-09-21 | 2020-09-21 | 3 | 3 | 0 | Supriya Sinha | Completed
| Swagger(Implement and check API if it is working ) |  | 2020-09-22 | 2020-09-22 | 3 | 3 | 0 | Supriya Sinha | Completed
| Code Review Code Convention and Coding Quality Should be checked |  | 2020-09-23 | 2020-09-23 | 3 | 3 | 0 | Aman Bharti, Sujoy Basak, Shubham Debnath | Completed
| Unit Test Positive case:- ReturnList(Returns the list of Questions) Negative Case:- ReturnListWithoutInput(We donot provide any input) |  | 2020-09-23 | 2020-09-24 | 15 | 15 | 0 | Supriya Sinha | Completed
| Integration Testing Check whether other services are working together or not |  | 2020-09-25 | 2020-09-25 | 3 | 3 | 0 | Aman Bharti, Sujoy Basak, Shubham Debnath,Supriya Sinha | Completed
| Prod Deployment Deploument to Azure,Dockerize,Deploy to Kubernatics |  | 2020-09-26 | 2020-09-28 | 12 | 0 | 12 | Supriya Sinha | Not Started
Audit Benchmark Module AC : Provide me a list of acceptable number of NO for different audit types | Create Repository :- BenchmarkRepo GetNolist(): HttpGet for retrieve the acceptbale number of No |  | 2020-09-21 | 2020-09-21 | 3 | 3 | 0 | Aman Bharti | Completed
| Create End Point:- AuditBenchmark Get(): HttpGet for invoking BenchmarkRep Log4Net for logging |  | 2020-09-21 | 2020-09-21 | 3 | 3 | 0 | Aman Bharti | Completed
| In Memory Database (Create Certain Conditions) |  | 2020-09-21 | 2020-09-21 | 3 | 3 | 0 | Aman Bharti | Completed
| Swagger(Implement and check API if it is working ) |  | 2020-09-22 | 2020-09-22 | 3 | 3 | 0 | Aman Bharti | Completed
| Code Review Code Convention and Coding Quality Should be checked |  | 2020-09-23 | 2020-09-23 | 3 | 3 | 0 | Sujoy Basak, Supriya Sinha, Shubham Debnath | Completed
| Unit Test Positive Test:- GetBenchmarkTest(Returns the list of conditions) Negative Test:- |  | 2020-09-23 | 2020-09-24 | 15 | 15 | 0 | Aman Bharti | Completed
| Integration Testing Check whether other services are working together or not |  | 2020-09-25 | 2020-09-25 | 3 | 3 | 0 | Aman Bharti, Sujoy Basak, Shubham Debnath,Supriya Sinha | Completed
| Prod Deployment Deploument to Azure,Dockerize,Deploy to Kubernatics |  | 2020-09-26 | 2020-09-28 | 12 | 0 | 12 | Aman Bharti | Not Started
Audit severity module AC : Gets the audit request from the user and give a response as per the conditions provided by the audit benchmark module | Create Repository :- BenchmarkRepo GetNolist(): HttpGet for retrieve the acceptbale number of No |  | 2020-09-21 | 2020-09-22 | 3 | 3 | 0 | Subham Debnath | Completed
| Create End Point:- AuditSeverity GetNumberOfNo(): HttpPost to get AuditResponse Log4Net for logging |  | 2020-09-21 | 2020-09-22 | 13 | 13 | 0 | Shubham Debnath | Completed
| Swagger(Implement and check API if it is working ) |  | 2020-09-22 | 2020-09-22 | 4 | 4 | 0 | Shubham Debnath | Completed
| Code Review Code Convention and Coding Quality Should be checked |  | 2020-09-23 | 2020-09-23 | 3 | 3 | 0 | Sujoy Basak, Supriya Sinha, Aman Bharti | Completed
| Unit Test Positive Case:- GetResponseTest(Returns the Response) Negative Case:- GetResponseWithoutInput(Do not return any response) |  | 2020-09-23 | 2020-09-24 | 15 | 15 | 0 | Shubham Debnath | Completed
| Integration Testing Check whether other services are working together or not |  | 2020-09-25 | 2020-09-25 | 3 | 3 | 0 | Aman Bharti, Sujoy Basak, Shubham Debnath,Supriya Sinha | Completed
| Prod Deployment Deploument to Azure,Dockerize,Deploy to Kubernatics |  | 2020-09-26 | 2020-09-28 | 12 | 0 | 12 | Shubham Debnath | Not Started
Authorization AC : It'll Generate a JWT token if the credentials match | Create Repository :- LoginRep CheckLoginCred(): Checks whether login credentials are correct or not |  | 2020-09-21 | 2020-09-21 | 3 | 3 | 0 | Sujoy Basak | Completed
| Create End Point:- Auth GetToken(): HttpPost returns token for valid details GenerateToken(): Returns a token Log4Net for logging |  | 2020-09-21 | 2020-09-22 | 13 | 13 | 0 | Sujoy Basak | Completed
| In Memory Database (Create Login Credentials) |  | 2020-09-22 | 2020-09-22 | 3 | 3 | 0 | Sujoy Basak | Completed
| Swagger(Implement and check API if it is working ) |  | 2020-09-22 | 2020-09-22 | 3 | 3 | 0 | Sujoy Basak | Completed
| Code Review Code Convention and Coding Quality Should be checked |  | 2020-09-23 | 2020-09-23 | 3 | 3 | 0 | Aman Bharti, Supriya Sinha, Shubham Debnath | Completed
| Unit Test Positive Case:- GetTokenTest(Returns the Token) Negative Case:- GetTokenWithoutID(No Token will Generate) |  | 2020-09-23 | 2020-09-24 | 15 | 15 | 0 | Sujoy Basak | Completed
| Integration Testing Check whether other services are working together or not |  | 2020-09-25 | 2020-09-25 | 3 | 3 | 0 | Aman Bharti, Sujoy Basak, Shubham Debnath,Supriya Sinha | Completed
| Prod Deployment Deploument to Azure,Dockerize,Deploy to Kubernatics |  | 2020-09-26 | 2020-09-28 | 12 | 0 | 12 | Sujoy Basak | Not Started
Audit management portal AC1: Login page to check the credentials AC2: View of Home Page where both Audit checklist and Audit Request will be there AC3: View of Audit Checklist to show the questions according to the type AC4: View of Audit Request to give the details and in return get the reponse | Login Page |  | 2020-09-24 | 2020-09-24 | 4 | 4 | 0 | Sujoy Basak | Completed
| Home Page |  | 2020-09-24 | 2020-09-24 | 5 | 5 | 0 | Sujoy Basak | Completed
| Audit Checklist Page |  | 2020-09-24 | 2020-09-24 | 9 | 2 | 7 | Aman Bharti | Completed
| Audit Form Page |  | 2020-09-25 | 2020-09-25 | 3 | 3 | 0 | Supriya Sinha | Completed
| Audit Response Page |  | 2020-09-25 | 2020-09-25 | 3 | 3 | 0 | Sujoy Basak | Completed
| Code Review Code Convention and Coding Quality Should be checked |  | 2020-09-28 | 2020-09-28 | 3 | 0 | 3 | Shubham Debnath,Supriya Sinha,Aman Bharti | Not Started
| End to End Testing Check whole code by keeping MVC in local machine and microservices in cloud |  | 2020-09-29 | 2020-09-30 | 18 | 0 | 18 | Sujoy Basak,Shubham Debnath, Aman Bharti, Supriya Sinha | Not Started