## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Claims Module AC1 : It'll give me status of specific claim when provided with claim id, policy id and member id AC2: It will allow me to validate the eligibility of claim and update the claim status in the db | Create Repository :-
ClaimStatusRepo
GetClaimStatus(): HttpGet for retrieving claim status StoreClaimStatus(): HttpPost for Storing Claim status
Create End Point:- /getClaimStatus GetClaimSatus(): HttpGet for invoking ClaimStatusRepo /submitClaim submitClaim(): Http post method for submiting a claim. Log4Net/slf4j for logging
Local Database / In Memory Database (To store claim details/ status)
Swagger(Implement and check API if it is working )
Code Review Code Convention and Coding Quality Should be checked
Unit Test Positive cases:- -------------------------------------- Positive test cases for the method that retrieve the claim status and the method that validate and submit the claim Negative Cases:- ------------------------------------ Negative test cases for methods that retrieve the claim status and the method which validate and submit the claim
Integration Testing:- Check whether other services are working together or not
Prod Deployment Deployment to Cloud
Member Module AC1 : It will allow me to view the premium bills AC2 : It will allow me to submit a new claim AC3 : It will allow me to view the status of a claim which is already submitted. | Create Repository :-
MemberPremiumRepo
GetPremiumBills(): method for getting the premium bills of a specific policy
Create End Point:-
/viewBills
getBills(): Http Get for retrieving the premium bills of a specific policy
/submitClaim
submitClaim(): Http Post for submitting a new claim
/getClaimStatus
getClaimStatus(): Http Get for retrieving status of an already submitted claim
Log4Net/Slf4j for logging
Local/In Memory Database (for storing member details, member policy details and member premium details)
Swagger(Implement and check API if it is working )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:-
Positive test cases fo the methods which performs the following operations. 1. Method which retrieves the premium bills. 2. Method which submits the new claim. 3. Methow which retrieves the status of the claim which is already submitted.
Negative Test:- Negative test cases fo the methods which performs the following operations. 1. Method which retrieves the premium bills. 2. Mthod which submits the new claim. 3. Methow which retrieves the status of the claim which is already submitted.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Policy Module AC1 : It provides me the list of providers where the healthcare services can be offered. AC2 : It provides me the list of benefits a member is eligible for under a subscribed policy. AC3: It provides me the eligible claim amount for the given benefit under a subscribed policy. | Create Repository :-
PolicyRepo
Method to retrieve the list of providers where the healthcare services can be offered (chain of hospitals)
Method to retrieve the list of benefits a member is eligible for under a subscribed policy
Method to retrieve the claim amount for the given benefit under a subscribed policy
Create End Point:-
/getChainOfProviders
Http GET method to get the list of permissible providers
/getEligibleBenefits
Http GET method to retrieve the list of benefit a member is eligible for under a subscribed policy
/getEligibleClaimAmount
Http GET method to retrieve the eligible claim amount for the given benefit under a subscribed policy
Log4Net/Slf4j for logging
Local/In Memory database for storing Policy Details, Member policy details, provider policy details
Swagger(Implement and check API if it is working )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the following methods: 1. Method that retrieves the list of permissible providers. 2. Method that retrieves the list of benefit that a member is eligible to under a subscribed policy. 3. Method that retrieves the eligible claim amount for the given benefit under a subscribed policy.
Negative Case:-
Negative test cases for the following methods:
1. Method that retrieves the list of permissible providers. 2. Method that retrieves the list of benefit that a member is eligible to under a subscribed policy. 3. Method that retrieves the eligible claim amount for the given benefit under a subscribed policy.
GetResponseWithoutInput(Do not return any response)
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization AC : It'll Generate a JWT token if the credentials match | Create Repository :-
LoginRepo
Create a method that Checks whether login credentials are correct or not
Create End Point:-
/Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Implement and check API if it is working )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Member portal AC1: Login page to check the credentials AC2: View of Home Page where options for viewing the bill status, verifying the claim status and submitting a new claim. AC3: View of bill status AC4: View for the claim status AC5: view to submit a new claim | Login Page
Home Page
Bill status page
Claim status page
View for submitting a new claim
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in local/cloud environment.