## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Loan Management Module | Create Repository :-
LoanRepository
AC1 : It will enable the user to retrieve the loan details based on the loan id
Method for retrieving the loan details based on the loan id
AC2 : It will enable me to save the collateral details by calling Collateral Management Microservice | Create End Point:-
/getLoanDetails
Define Http GET method for retrieving the loan details based on loan id
/saveCollaterals
Define Http POST method for saving the collaterals(By calling Callateral Management Microservice)
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Loan, Customer_Loan, and Customer)
Swagger(Implement and check API if it is working )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive case:-
Write positive test cases for the methods which perform the below operations. 1. Method that retrieves loan details based on the loan id. 2. Method that saves the collaterals
Negative Case:-
Write nagative test cases for the methods which perform the below operations. 1. Method that retrieves loan details based on the loan id. 2. Method that saves the collaterals
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Collateral Management Module | Create Repository :-
CollateralRepository
AC1 : Provides collateral details when provided with loan id and customer id
AC2 : Provides the way for saving the collateral details | Define a method for retrieving the collateral details when provided with loan id and customer id
Define a method for saving the collateral details
Create End Point:-
/getCollaterals
Define a method that responds to HTTP GET method for retrieving the details of the collaterals
/saveCollaterals
Define a method that responds to HTTP Post Method for saving the collateral details
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Collateral_Loan, Collateral_RealEstate and Collateral_CashDeposits)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:-
Positive test cases to be written for the below mentioned methods: 1. Method that retrieves the collateral details. 2. Method that saves the collateral details
Negative Test:- Positive test cases to be written for the below mentioned methods: 1. Method that retrieves the collateral details. 2. Method that saves the collateral details
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment
Risk Assessment Module | Create Repository :-
RiskAssessmentRepo
AC : Enables us to view risks of the collaterals held by the bank.
Define a method that retrieves the risk of collaterals held by the bank.
Create End Point:-
/getCollateralRisk
Define an Http POST method to get Collateral risk for a given loan id by interacting with the Collateral management module.
Log4Net/Slf4j for logging
Local/In memory database for storing Collateral_Risk and Collateral_MarketValue
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Create positive test cases for the method that retrieves the risk of collaterals held by the bank.
Negative Case:-
Create negative test cases for the method that retrieves the risk of collaterals held by the bank.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Collateral Loans Portal | Login Page
AC1: Login page to check the credentials
Home Page
AC2: View of Home Page where options for viewing the Loan Details, Saving the collaterals of a Sanctioned loan and viewing the risk associated with the collateral. | Loan Details page
Page for accepting and saving collaterals
AC3: View of Loan Details | Collateral risk page
Code Review
AC4: View for accepting and saving collaterals | Code Convention and Coding Quality Should be checked
End to End Testing
AC5: View of Collateral risk | Check whole code by keeping MVC in local machine and microservices in cloud