## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Offers Module | Create Repository :-
OffersRepository
AC1 : It will enable the user to post a new offer
AC2 : It will enable the user to edit an existing offer AC3 : It will enable user to engage an offer AC4 : It will enable user to view the offer status when provided with the offer id AC5: It will enable the user to view the offers by category AC6: It will enable the user to view the offers by posted Date AC7: It will enable the user to view the offers by top 3 likes in the category | Method for storing new offers. Method for editing an existing offer. Method for engaging an Offer. Method for retrieving the Offer status by offer id Method for retrieving the Offers by Category Method for retrieving the Offers by posted date. Method for retrieving the offers by top 3 likes in a category
Create End Point:-
/getOfferDetails
Http GET method for viewing the Offer details by offer id
/getOfferByCategory
Http GET method for viewing the Offers by category
/getOfferByTopLikes
Http GET method for viewing the Offers by top 3 likes.
/getOfferByPostedDate
Http GET method for viewing the Offers by posted date.
/engageOffer
Http POST method for engaging an Offer
/editOffer Http PUT method for editing an Offer.
/addOffer Http POST method for adding a new Offer.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Offer and Offer_Category)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive case:-
Write Positive test cases for all the methods identified with a target of 100% code coverage
Negative Case:-
Write negative test cases for the methods identified with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Employee Module | Create Repository :-
EmployeeRepository
AC1 : It enables to view the Offers posted by an employee. | Method for retrieving the Offers posted by an employee
AC2 : It enables to view the most liked Offers by an employee | Method for retrieving the most liked offers by an employee
AC3 : It enables to view the Profile of the employee. | Method for retrieving the profile of the employee.
Create End Point:-
/viewEmployeeOffers
Http GET method for viewing the offers posted by an employee.
/viewMostLikedOffers
Http GET method for viewing the top 3 most liked offers by an employee.
/viewProfile
Http GET method for viewing the profile of the employee.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Employee and Employee_Offers)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:-
Positive test cases for the methods identified for the microservice with a target of 100% code coverage
Negative Test:- Negative test cases for the methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment
Points Module | Create Repository :-
PointsRepo
AC1 : Enables to refresh the points gained by the employee for the posts
Define a method to retrieve the points gained by an employee
AC1 : Enables view the points gained by an employee | Create End Point:-
/getPointsOfEmployee
Define an Http GET method to view the points gained by an employee.
/refreshPointsOfEmployee
Define an Http POST method to refresh the points gained by an employee
Log4Net/Slf4j for logging
Local/In memory database(for storing Employee_Points)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Create positive test cases for the methods identified for the microservice with a target of 100% code coverage
Negative Case:-
Create negative test cases for the methods identified for the microservice with the target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Corporate Classsifieds Portal | Login Page
AC1: Login page to check the credentials
Home Page
AC2: View of Home Page with the following options. 1. Post an Offer. 2. Edit a posted Offer. 3. Engage an Offer. 4. View the offers Posted by Self. 5. View recently liked offers. 6. Views Offers based on Category, posted date, top likes etc. 7. View Profile | Page for posting an Offer
Page for editing an offer
AC3: View for posting and Offer | Page for engaging an offer
Page for viewing recently liked offers
AC4: View for editing an offer | Page for Viewing the Offers based on category, posted date, top likes etc.
Page for viewing the Profile
AC5: view for engaging an offer | Code Review
Code Convention and Coding Quality Should be checked
AC6: View of recently liked offers | End to End Testing
AC5: View of Collateral risk AC6: Views for Offers based on Category, posted date, top likes etc. AC7. View for profile AC8: Views for Offers posted by Self | Check whole code by keeping MVC in local machine and microservices in cloud