## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
IPTreatmentOffering Module AC1 : It will enable the user to view the list of service packages for international patients. AC2 : It will enable the user to view the List of specialists along with their experience and contact detail | Create Repository :- InPatientRepo Method for retrieving the list of service packages for international patients. Method for retreiving the Package Details by package name. Method for retrieving the list of specialists with their experience and contact details.
Create End Point:-
/IPTreatmentPackages Define Http GET method for viewing the list of service packages for international patients. /IPTreatmentPackageByName Define Http GET method for viewing the Package details by package name. /Specialists Define Http GET method for viewing the list of specialists.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing AilmentCategory, PackageDetail, SpecialistDetail)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
IPTreatment Module AC: It should enable the new international patient to get a timetable of consulation by specialist based on ailment. | Create Repository :- IPTreatmentRepo Method to store patient details along with the package and specialist details
Create End Point:- /FormulateTreatmentTimetable Define HTTP GET method that returns the treatment plan for the patient.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing PatientDetails, and TreatmentPlan)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment
InsuranceClaim Module AC1 : It should enable the admin user to retrieve the list of Insurance agencies with their limits and duration for claim processing. AC2: It should enable the admin user to choose a patient whose treatment is in-progress and can be marked as complete. AC3: It should enable the admin user to furnish all the neccessary details from the hospital to process the claim once the insurer is is selected. AC4: It should enable the admin user to retrieve the insurer details based on the package name. | Create Repository :- InsuranceClaimRepo Method to retrieve the list of insurance agencies Method to retrieve the Insurer details based on package name. Method to store Initiate claim details
Create End Point:- /getAllInsurerDetail Define HTTP GET method to get the details of the Insurance agencies. /getInsurerByPackageName Define HTTP GET method to get the details of the insurer by package name. /initiateClaim Define HTTP POST method for storing InitiateClaim details.
Log4Net/Slf4j for logging
Local/In memory database(for storing InsurerDetail and InitiateClaim)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
IP Treatment Management Portal AC1: Login page to check the credentials AC2: View of Home Page with the options for viewing the list of service offering, Option to choose a package for a patient and view the treatment plan, View the list of registered patients, Choose the patient to mark treatment completion. AC3 : View of the list of service offering as package of treatment. AC4: View of the treatment plan. AC5: View for the list of Patients. AC6: View for choosing the insurer and package for claim. | Login Page
Home Page
Service Offering list page
Registered Patient list page
Patient selection page for marking treatment completion.
Page for choosing insurer and package for claim
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud