## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Drugs Module AC1 : It should enable the user to Search Drugs by Name/ID AC2 : It should enable the user to get dispatchable stock of a drug by location. | Create Repository :- DrugsRepo Method for retrieving the drugs details by Id Method for retreiving the drugs details by name Method for retrieving the dispatchable stock available for a given drug in the given location.
Create End Point:- /searchDrugsByID Define Http GET method for getting the drug details by id. /searchDrugsByName Define Http GET method for getting the drug details by name. /getDispatchableDrugStock Define Http POST method for getting the drug details and stock available for dispatch in a given location.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Drug, DrugLocation)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Subscription Module AC1: It should enable the user to subscribe for mail-order pharmacy. AC2: It should enable the user to unsubscribe from mail-order pharmacy | Create Repository :- SubscriptionRepo Method to store Member Prescription details Method for storing Member subscription details.
Create End Point:- /subscrribe Define HTTP POST method for subscribing to Mail-Order pharmacy. /unsubscribe Define HTTP POST method for unsubscribing from Mail-Order pharmacy.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing MemberPrescription and MemberSubscription)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Refill Module AC1 : It should enable to view the last refill status for a given subscription AC2: It should enable the user to get the prescriptions that are due for refill. AC3: It should enable the user to take adhoc refill order for subscription based on the availability of drugs based on a given location. | Create Repository :- RefillRepo Method to retrieve the latest refill status of a subscription. Method to retrieve the details of the subscriptions that are due for refill Method to store details of adhoc refill order details.
Create End Point:- /viewRefillStatus Define HTTP GET method to get the latest refill status of a given subscription /getRefillDuesAsOfDate Define HTTP GET method to get the details of the subscriptions due for refill as of a given date. /requestAdhocRefill Define HTTP POST method for accepting and storing adhoc refill request.
Log4Net/Slf4j for logging
Local/In memory database(for storing RefillOrder and RefillOrderLineItem)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Member Portal AC1: Login page to check the credentials AC2: View of Home Page with the options for viewing the options for 1) Subscribe/Unsubscribe a prescription for refill orders. 2) View Drugs that are supported. 3) View Refill status 4) View Refills that are due for the member. 5) Request and adhoc refill. AC3 : View for Subscribe/Unsubscribe a prescription. AC4: View for the drugs that are supported AC5: View of Refill status AC6: View of refills that are due for a member AC7: View for accepting adhoc refill request for a subscription | Login Page
Home Page
subscribe/unsubscribe page
Supported drugs Page
Refill status page
Refill due page
Adhoc refill request page
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud