## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Supplier Module AC1 : It should enable the user to get the potential suppliers for a given part with feedback rating. AC2 : It should enable the user to add a new supplier. AC3: It should enable the user to edit the supplier details. AC4: It should enable the user to update the feedback details of a supplier. | Create Repository :- SupplierRepo Method for retrieving the supplier details. Method for storing new supplier details with the details of the part supplied by the supplier Method for editing the supplier details. Method for updating feedback details of a supplier
Create End Point:- /getSupplierOfPart Define Http GET method for getting the supplier details for a given part /addSupplier Define Http POST method for adding new supplier details. /editSupplier Define Http PUT method for editing the supplier details. /updateFeedback Define HTTP PUT method for updating the feedback details of a supplier
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Supplier, SupplierPart)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Plant Module AC1: It should enable the user to view the re-order point of any part as of date AC2: It should enable the user to view the stock in hand of a given part as of date. AC3: It should enable the user to update the min/max quantity of a part based on the assembly demand of the plant. | Create Repository :- PlantRepo Method to retrieve the details of the parts that needs to be re-ordered. Method to retrieve the stock in hand of a given part as of date. Method to update the min/max quantity of a given part.
Create End Point:- /viewPartsReOrder Define HTTP GET method for viewing the details of the parts that needs to be re-ordered. /viewStockInHand Define HTTP GET method viewing the stock in hand of a given part. /updateMinMaxQuantities Define HTTP PUT method for updating the min/max quantity of a given part.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Part, Demand, ReorderRules and PlantReorderDetails)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
RFQ Module AC1 : It should enable the user to get the RFQ for parts. AC2: It should enable the user to get the potential vendors for each part to circulate the RFQ. | Create Repository :- RFQRepo Method to store the RFQ deails.
Create End Point:- /getRFQOfPlant Define HTTP GET method to get the RFQ of parts. /getPotentialVendorsOfRFQ Define HTTP GET method to get the potential vendors for each part to circulate the RFQ.
Log4Net/Slf4j for logging
Local/In memory database(for storing RFQ)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Fabricate Portal AC1: It should enable the member to view Stock details, Part requirements, Min/Max quantities/Re-Order points. AC2: It should enable the user to update Min/Max quantities of a part and refresh the Re-order points. AC3: It should enable the user to View and Update Supplier details AC4: It should enable the user to provide feedback rating for the supplier. AC4: It should enable the user to get RFQ details. AC5: It should enable the user to get potential suppliers of RFQ | Login Page
Home Page
Pages for displaying stock requirements, Part requirements, Reorder points
Page for updating Min/Max quantities
Supplier view/update pages
supplier feedback update page
RFQ Details page
Supplier listing for RFQ page
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud