## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Process Pension Module AC1 : It should enable the user to accept pensioner details and view the pension details. AC2 : I should enable the user to process the pension if provided with the aadhar no and pension amount. | Create Repository :- ProcessPensionRepo Method for storing pension details.
Create End Point:- /PensionDetail Define Http GET method for getting the pension details for a given pensioner. /ProcessPension Define Http POST method for processing pension when provided with Aadhar number and pension amount.
Log4Net/Slf4j for logging
Local/In Memory Database(for storing PensionDetail)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Pensioner Detail Module AC: It should enable the user to view the pensioner details when provided with the aadhar number. | Create Repository :- PensionerDetailsRepo Method to retrieve the pensioner details which takes aadhar number as parameter.
Create End Point:- /PensionerDetailByAadhaar Define HTTP GET method for viewing the pensioner details when provided with the aadhar number.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing PensionerDetail)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Pension Disbursement Module AC: It will enable to get the status code indicating success or failure after processing the pension when provided with ProcessPensionInput (Aadhar number, pension amount and Bank service charge) | Create Repository :-
Create End Point:- /DisbursePension Define HTTP POST method to process the pension and return the appropriate status code.
Log4Net/Slf4j for logging
Local/In memory database
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization Module | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Pension Management Portal AC1: It should enable the user to login to the portal AC2: It should enable the user to view the home page once successully signed in. AC3: It should enable the user to provide the pensioner details. AC4: It should enable the user to process the pension after proper validation of data and store the pension details in the database. | Login Page
Home Page
Pages for accepting the pensioner details
view for displaying pension amount
Success/error page
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud