## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Medicine Stock Module AC : It should enable the user retrieve and view the medicine details in the stock | Create Repository :- MedicineStockRepo Method for retrieving the medicine details in the stock.
Create End Point:- /MedicineStockInformation Define Http GET method for getting the medicine details in the stock
Log4Net/Slf4j for logging
Local/In Memory Database (For storing MedicineStock)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Medical representative schedule Module AC: It should enable the user create and view the medical representative schedule for meeting doctors | Create Repository :- MedicalRepScheduleRepo Method to store the medical representative schedule.
Create End Point:- /RepSchedule Define HTTP GET method for viewing the medical representative schedule for meeing doctors when provided with the start date.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing RepSchedule)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Pharmacy Supply Module AC1 : It should enable the user to find the final demand of medicine that can be supplied to its pharmacists. | Create Repository :- PharmacySupplyRepo Method to store MedicineDemand Method to store PharmacyMedicineSupply Method to retrieve list of pharmacies.
Create End Point:- /PharmacySupply Define HTTP GET method to view PharmacyMedicineSupply
Log4Net/Slf4j for logging
Local/In memory database(for storing MedicineDemand, PharmacyMedicineSupply, Pharmacy)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Pharmacy medicine supply portal AC1: It should enable the user to login to the Pharmacy Medicine supply portal. AC2: It should enable the user to view the home page once successfully signed in. AC3: It should enable the user to view the schedule for the medical representative for doctors meet. AC4: It should enable the user to view the medicine count to be distributed to its pharmacist. | Login Page
Home Page
Medical representative schedule page
Medicine Count page which display the medicine count for pharmacies
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud