## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Consumer Module AC1 : It should enable the user to create consumer business AC2 : It should enable the user to update consumer business. AC3 : It should enable the user to view consumer business. AC4 : It should enable the user to create business property. AC5 : It should enable the user to update business property. AC6 : It should enable the user to view business property. | Create Repository :- ConsumerRepo Method for creating consumer business. Method for updating consumer business. Method for viewing consumer business. Method for creating business property. Method for updating business property. Method for viewing business property.
Create End Point:- /createConsumerBusiness Define Http POST method for creating a consumer business resource. /updateConsumerBusiness Define Http PUT method for updating a consumer business resource. /createBusinessProperty Define Http POST method for creating a business property resource. /updateBusinessProperty Define HTTP PUT method for updating a business property resource. / viewConsumerBusiness Define an HTTP GET method for retrieving a consumer business resource. / viewConsumerProperty Define an HTTP GET method for retrieving a business property resource.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Consumer,Business, Property, PropertyMaster, BusinessMaster)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Policy Module AC1: It should enable the user to create a policy based on the business and property value. AC2: It should enable the user to issue a policy to the consumer based on the payment and acceptance status from the consumer. AC3: It should enable the user to view the policy details. AC4: It should enable the user to get the policy quote based on the business value and property value. . | Create Repository :- PolicyRepo Method to retrieve the details from the policy master Method to store the consumer policy Method to retrieve the consumer policy.
Create End Point:- /createPolicy Define HTTP POST method for creating a new Policy /issuePolicy Define HTTP POST method issuing a policy to a consumer /viewPolicy Define HTTP GET method for viewing a policy details. /getQuotes Define HTTP GET method for getting a policy quote based on the business value and property value.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing PolicyMaster, ConsumerPolicy)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Quotes Module AC1 : It should enable the user to get a policy quote based on the business and property value. | Create Repository :- QuoteRepo Method to retrieve details from the Quote Master.
Create End Point:- /getQuotesForPolicy Define HTTP GET method to get the quote for a policy.
Log4Net/Slf4j for logging
Local/In memory database(for storing QuoteMaster)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization Module | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Insureity Portal AC1: It should enable agent to sign into the portal. AC2: It should enable the agent to view the home page once successfully signed in. AC3: It should enable the agent to create, edit and view consumer businesses and properties. AC4: It should enable the agent to create a policy. AC5: It should enable the agent to issue the policy based on the payment information and acceptance by the customer. AC6: It should enable the agent to view the policy. | Login Page
Home Page
Pages for creating, editing and viewing consumer businesses and properties.
Create policy page
Policy issue page
View policy page
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud