## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Daily Share Price Module AC1 : It should enable the user to get the daily share price of a stock | Create Repository :- SharePriceRepo Method for retrieving daily share price of a stock.
Create End Point:- /dailySharePrice Define Http GET method for retrieving the daily share price.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing StockDetails)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Daily Mutual Fund NAV Module AC1: It should enable the user to Get NAV value of a Mutual Fund . | Create Repository :- MutualFundRepo Method to retrieve the mutual fund details.
Create End Point:- /mutualFundNav Define HTTP GET method to get the mutual fund details
Log4Net/Slf4j for logging
Local/In Memory Database (For storing MutualFundDetails)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Calculate Net worth Module AC1 : It should enable the user to calculate the current value of share holdings and mutual fund holdings and find out the net worth. AC2: It should enable the user to sell the assets and calculate the final net worth. | Create Repository :- QuoteRepo Method to retrieve Portfolio details. Method to retrieve the stock details. Method to retrieve the mutual fund details.
Create End Point:- /calculateNetworth Define HTTP GET method to get the net-worth of a customer portfolio. /sellAssets Define the HTTP POST method to sell the assets and get the balance net-worth.
Log4Net/Slf4j for logging
Local/In memory database(for storing PortfolioDetails, StockDetails, MutualFundDetails)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization Module | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Customer Portal AC1: It should enable agent to sign into the portal. AC2: It should enable the agent to view the home page once successfully signed in. AC3: It should enable the user to view net-worth of his/her investment portfolio AC4: It should enable the user to sell existing assets and view the final net-worth. | Login Page
Home Page
Net-worth view page.
Assets selling / balance net-worth page
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud