## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Account Management Module AC1 : It should enable the user to create an account for a customer. AC2: It should enable the user to get the accounts related to a customer. AC3: It should enable the user to fetch the details of a specific account. AC4: It should enable the user to get the account statement for a particular account. AC5: It should enable the user to deposit to an account AC6: It should enable the user to withdraw from an account. | Create Repository :- AccountRepo Method for storing Account details. Method for retrieving Account details. Method for fetching account statement.
Create End Point:- /createAccount Define Http POST method for creating a new account. /getCustomerAccounts Define HTTP GET method for fetching the account related to a specific customer. /getAccount Define HTTP GET method to fetch details regarding to a specific account. /getAccountStatement Define HTTP GET method to statement for a particular account. /deposit Define HTTP POST method for depositing amount in to an account. /withdraw Define HTTP POST method for withdrawing amount from an account.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Account, Statement)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Customer Module AC1: It should enable the user to create a new customer. AC2: It should enable the user to view profile of a specific customer. . | Create Repository :- CustomerRepo Method to retrieve the customer details. Method to store the customer details.
Create End Point:- /createCustomer Define HTTP POST method to create a new customer resource. /getCustomerDetails Define HTTP GET method to retrieve the details of a specific customer
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Customer)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Transactions Module AC1 : It should enable the user to deposit an amount to an account. AC2: It should enable the user to withdraw an amount from an account. AC3: It should enable the user to transfer an amount from one account to another. AC4: It should enable the user to get the transaction details of a specific customer. | Create Repository :- TransactionRepo Methods for storing transaction details Methods for retrieving transaction details
Create End Point:- /deposit Define HTTP POST method to deposit an amount into an account /withdraw Define HTTP POST method to withdraw an amount from an account. /transfer Define HTTP POST method for transfering an amount from one account to another. /getTransactions Define HTTP GET method for fetching the transaction details of a customer
Log4Net/Slf4j for logging
Local/In memory database(for storing Transaction History Data Model)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Rules Module AC1: It should enable the user to evaluate minimum balance. AC2: It should enable the user to fetch the service charge applicable to minmum balance accounts | Create Repository :-
Create End Point:- /evaluateMinBal Define HTTP GET method for fetching the RuleStatus regarding the minimum balance. /getServiceCharges Define HTTP GET method to fetch the service charge applicable to a minimum balance account.
Log4Net/Slf4j for logging
Local/In Memory Database
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Authorization Module | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Bank Portal AC1: It should enable user to sign into the portal. AC2: It should enable the user to view the home page once successfully signed in. AC3: It should enable the customer to view his accounts and balances. AC4: It should enable the Customer to Deposit an amount into his account AC5: It should enable the Customer to withdraw an amount from his account. AC6: It should enable the customer to view his bank statements. AC7: It should enable the customer to view his transactions. AC8: It should enable the Employee to create Customers and accounts | Login Page
Home Page
Account view page
Deposit and withdrawal pages
bank statement page
transactions page
Customer/Account creation page
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud