## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Products Module AC1 : It should enable the customer to get the product by id. AC2: It should enable the customer to get the product by name. AC3: It should enable the customer to add a rating to a product | Create Repository :- ProductRepo Method for retrieving the product by id. Method for retrieving the product by name. Method to add a rating to a product
Create End Point:- /searchProductById Define Http GET method for viewing the product by id. /searchProductByName Define HTTP GET method for viewing the product by name. /addProductRating Define HTTP POST method for adding a rating to a product.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Product)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
ProceedToBuy Module AC1: It should enable the customer to add a product to the cart. AC2: It should enable customer to add a product to the wishlist when the product is not available. . | Create Repository :- ProceedToBuyRepo Method to store product to the cart. Method to store product to the wishlist. Method to retrieve the details from the cart.
Create End Point:- /addProductToCart Define HTTP POST method to add a product to the cart. /addProductToWishlist Define HTTP POST method to add a product to the wishlist.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing Cart, VendorWishlist)
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Vendor Module AC1 : It should enable the user to fetch a list of vendors for a given product. | Create Repository :- VendorRepo Method to retrieve Portfolio details. Method to retrieve the list of vendors for a given product.
Create End Point:- /getVendorDetails Define HTTP GET method view the list of vendors for a given product.
Log4Net/Slf4j for logging
Local/In memory database(for storing vendor, VendorStock)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization Module | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
e-Commerce Portal AC1: It should enable customer to sign into the portal. AC2: It should enable the customer to view the home page once successfully signed in. AC3: It should enable the customer to serach the product by id or name. AC4: It should enable the customer to key in the zip code and exptected delivery date in the product page. AC5: It should enable the customer to add the product to the cart by choosing "procceed to buy" option. AC6: It should enable the customer to add the product to the wishlist if the product is out of stock. AC7: It should enable the user to view the Product details in the checkout page. AC8: It should enable the cusotmer to rate a product. | Login Page
Home Page
Product search page
checkout page
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud