## Sheet1
User Story | Task | Story Point | Start Date | End Date | Estimated hour | Hour Burn | Remaining Hour | Assigned | Status
Component processing Module AC1 : It should enable the user to determine if the request is for repair or replacement. AC2: It should enable the user to determine the repair/replacement cost along with the consideration if it is a priority request. AC3: It should enable the user to determine the cost and date of delivery. AC4: It should enable the user to view the processing response. | Create Repository :- ComponentProcessingRepo Method for storing Process Request Method for storing Process Response.
Create End Point:- /ProcessDetail Define HTTP GET method for processing the request for repair/replacement. /CompleteProcessing Define HTTP POST method for interacting with the payment module and completing the processing of repair/replacement request.
Log4Net/Slf4j for logging
Local/In Memory Database (For storing ProcessRequest, ProcessResponse)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive case:- Write positive test cases for the methods identified in the microservice with a target of 100% code coverage. Negative Case:- Write negative test cases for the methods identified in the microservice with a target of 100% code coverage.
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to local/cloud environment.
Packaging and Delivery module AC: It should enable user to detemine the packaging and delivery charge for an item based on the pre-defined logic and also determine the expected delivery date . | Create Repository :-
Create End Point:- /GetPackagingDeliveryCharge Define HTTP GET method determine the packaging and delivery charge along with the expected date of delivery.
Log4Net/Slf4j for logging
Local/In Memory Database
Swagger(Configure the microservice with Swagger for documentation )
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Test:- Write positive test cases for all the methods identified for the microservice with the target of 100% code coverage. Negative Test:- Write Negative test cases for all the methods identified for the microservice with the target of 100% code coverage.
Integration Testing Check whether other services are working together or not
Prod Deployment Deployment to Local/Cloud environment
Payment module AC1 : It should enable the user to accept the credit card details and total processing charge, deducts the processing charge and return the balance amount. | Create Repository :-
Create End Point:- /ProcessPayment Define HTTP GET method to process the payment by accepting the credit card number, credit limit and processing charge.
Log4Net/Slf4j for logging
Local/In memory database
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test Positive Case:- Create positive test cases for all methods identified for the microservice with a target of 100% code coverage Negative Case:- Create negative test cases for all methods identified for the microservice with a target of 100% code coverage
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Authorization Module | Create Repository :-
LoginRepo
AC : It'll Generate a JWT token if the credentials match
Create a method that Checks whether login credentials are correct or not
Create End Point:-
Auth
Http POST method that returns token for valid details
Log4Net/Slf4j for logging
Local/In Memory Database (Create Login Credentials)
Swagger(Configure the microservice with Swagger for documentation)
Code Review
Code Convention and Coding Quality Should be checked
Unit Test
Positive Case:-
Positive test cases for the method that returns JWT for valid credentials
Negative Case:-
Negative test cases for the method that returns JWT for valid credentials
Integration Testing
Check whether other services are working together or not
Prod Deployment
Deployment to Local/Cloud environment.
Return order portal AC1: It should enable user to sign into the portal. AC2: It should enable the customer to view the home page once successfully signed in. AC3: It should enable user to provide the details for return order. AC4: It should enable the user to view the processing details. AC5: It should enable the user to confirm processing. | Login Page
Home Page
page for providing the details of the order return
Procesing details page for viewing the processing details
Code Review
Code Convention and Coding Quality Should be checked
End to End Testing
Check whole code by keeping MVC in local machine and microservices in cloud